## Slide 1: Strategic Planning Update
October 23, 2012

## Slide 2: Presentation Overview
Strategic Plan 2010-13 Summary
Upcoming Activities

## Slide 3: Strategic Plan 2010-2013 Summary of Progress
Overall Summary
The 2010-2013 Strategic Plan contains four directions in the areas of student preparedness, transfer, resources, and innovation. There are 13 total goals contained in the plan; three goals each in the areas of student preparedness, transfer, and innovation. There are four goals in the area of resources.
For the current year, the plan contains a total of 32 objectives and 139 action steps across all of the goals. To date, nearly all of the objectives are in progress. Of the 139 action steps, 57% have been completed and 43% are in progress.

## Slide 4: Strategic Plan 2010-2013 Summary of Progress
Goal 1.1: 80% of all students who seek certificates, associate degrees, and declare transfer as a goal will be assessed, placed, and complete a professional education plan. | 
Summary of Objectives and Action Steps There are three objectives and 13 action steps associated with this goal. Fully implement MAP Fund the matriculation program Comprehensive and efficient system for assessment and testing | Status 3 of 3 objectives are still in progress 6 of 13 action steps are still in progress
Accomplishments Bugs have been corrected and MAP continues to be enhanced through regular meetings with IT staff. Funding has been secured to move to computerized assessment testing. | 
Areas of Focus 2012-13: Continue work related to MAP in order to maximize the number of educational plans completed outside of APSY classes. Continue to work toward establishing computerized assessment testing for students. | 

## Slide 5: Strategic Plan 2010-2013 Summary of Progress
Goal 1.2: Increase by 5% the number of individuals with an unidentified career goal who receive career assessment and job acquisition skills development services. | 
Summary of Objectives and Action Steps There is one objective and three action steps associated with this goal. Develop a comprehensive career, job, and life development program. | Status 1 of 1 objectives are still in progress 1 of 3 action items are still in progress
Accomplishments Program review and data analysis from other sources have been completed. | 
Areas of Focus 2012-13 Conduct a current state assessment of the Center for Career and Life Development. | 

## Slide 6: Strategic Plan 2010-2013 Summary of Progress
Goal 1.3: Improve the progression rate of students in math, English, and the ESL program sequence from levels 300 to 200 and from 200 to transfer courses by 5% in each level. | 
Summary of Objectives and Action Steps There are three objectives and 14 action steps associated with this goal: Develop comprehensive follow-up and retention plan for at-risk students Promote student completion of basic skills courses as outlined in educational plan Comprehensive tutoring plan | Status 3 of 3 objectives are still in progress 6 of 14 action items are still in progress
Accomplishments Individual faculty led projects have been completed. Tutoring programs for English and math 300 level courses have been completed through BSI. | 
Areas of Focus 2012-13 Continue to examine ways of identifying at-risk students and challenges that hinder success. | 

## Slide 7: Strategic Plan 2010-2013 Summary of Progress
Goal 2.1: Improve by 5% student transfers to four-year institutions. | 
Summary of Objectives and Action Steps There are three objectives and seven action steps associated with this goal: Establish a comprehensive stand-alone Transfer Center Create a system to support students in reaching their goal of transfer Establish a Teacher Preparation Center (PACT) | Status 2 of 3 objectives are in progress 4 of 7 action steps are in progress
Accomplishments A stand-alone transfer center has been established and will be further realized through the Gateway building. | 
Areas of Focus 2012-13 Continue to focus on understanding why some students are not reaching their goal of transfer as well as identifying teacher preparation students. | 

## Slide 8: Strategic Plan 2010-2013 Summary of Progress
Goal 2.2: Improve by 15% the number of students classified as transfer ready. | 
Summary of Objectives and Action Steps There are two objectives and six action steps associated with this goal: Expand and utilize technological resources to increase the number of transfer ready students Develop and implement a transfer ready outreach plan | Status 2 of 2 objectives are in progress 5 of 6 action steps are in progress
Accomplishments Partnerships with four-year universities have increased. | 
Areas of Focus 2012-13 Continue to focus on using technological resources to increase transfer readiness. Additionally, continue to focus on developing and implementing a transfer ready outreach plan. | 

## Slide 9: Strategic Plan 2010-2013 Summary of Progress
Goal 2.3: Increase by 20% the number of students in the Honors Program. | 
Summary of Objectives and Action Steps There are three objectives and 17 action steps associated with this goal: Match counseling services to increase in Honors students Develop class scheduling that better meets needs of Honors students Develop and implement an Honors outreach plan | Status 3 of 3 objectives are still in progress 7 of 17 action steps are still in progress
Accomplishments Several key operational activities were accomplished including: developing estimates of the number of hours needed for counselor meetings with transfer partners, honors events, and student visits. As well, the Honors program review was completed and an assessment of student satisfaction with the program. | 
Areas of Focus 2012-13 Working with Liberal Arts faculty to schedule permanent times for English 1A and 1B as well as Humanities 10A and 10B. | 

## Slide 10: Strategic Plan 2010-2013 Summary of Progress
Goal 3.1: Increase external foundation contributions to $1 million annually. | 
Summary of Objectives and Action Steps There are three objectives and 12 action steps associated with this goal: Establish and utilize a comprehensive alumni database Expand business and community partnerships Strengthen planned giving | Status 3 of 3 objectives are in progress 8 of 12 action items are in progress
Accomplishments Contributions to the Foundation have increased substantially. Additionally, many action items related to the alumni network have been completed and the long-range plan for the Foundation is currently in process. | 
Areas of Focus 2012-13 Continue to focus on action steps related to planned giving as well as completing the fundraising plan associated with developing the alumni network. Additionally, focus on developing the long-range plan for the Foundation and the Foundation Board. | 

## Slide 11: Strategic Plan 2010-2013 Summary of Progress
Goal 3.2: Realize a minimum of $1 million in savings per year through the implementation of college efficiencies. | 
Summary of Objectives and Action Steps There are two objectives and 10 action items associated with this goal: Increase grant funds Establish a comprehensive system to identify and implement college efficiencies on an annual basis | Status 1 of 2 objectives is in progress 4 of 10 action items are in progress
Accomplishments Grant related workshops and training have been implemented during in-service, a grant newsletter has been developed, and a grants manual has been approved and posted on the Grants website. | 
Areas of Focus 2012-13 The college will need to turn its attention to establishing a comprehensive system to identify and implement college efficiencies on an ongoing basis. | 

## Slide 12: Strategic Plan 2010-2013 Summary of Progress
Goal 3.3: Meet funding requirements to fulfill the “20-year Facilities and Scheduled Maintenance Plan.” | 
Summary of Objectives and Action Steps There are three objectives and 15 action items associated with this goal: Establish funding and construction plans for Science and TAS buildings. Meet funding requirements for 20-year Facilities and Scheduled Maintenance Plan. | Status 1 of 3 objectives are still in progress 3 of 15 action items are still in progress
Accomplishments Funding for the new Science building has been established as has funding for the new TAS building. | 
Areas of Focus 2012-13 Continue to focus on meeting funding requirements for 20-year Facilities and Scheduled Maintenance Plan. | 

## Slide 13: Strategic Plan 2010-2013 Summary of Progress
Goal 3.4: Improve the efficiency of college-wide communications and marketing strategies through a centralized system. | 
Summary of Objectives and Action Steps There are four objectives and 14 action steps associated with this goal: Enhance communication to include latest technology Integrate marketing and public relations into larger college community Create an innovative Visitors’ Center Campaign to increase high school’s recommending Saddleback College | Status 1 of 4 objectives are still in progress 14 of 14 action steps have been accomplished
Accomplishments The campaign to increase high school’s recommending Saddleback College has been completed; as have enhancements in technology to facilitate communication among faculty and staff. A plan has also been developed to better integrate marketing and public relations into the broader college community. | 
Areas of Focus 2012-13 Studies for the Visitors’ Center have been completed; continue to focus on creating the Visitors’ Center. | 

## Slide 14: Strategic Plan 2010-2013 Summary of Progress
Goal 4.1: Meet or exceed state targets for each Career Technical Education (CTE) Perkins Core Indicator. | 
Summary of Objectives and Action Steps There are two objectives and five action steps associated with this goal: Establish and implement a system to track student progress to completion Develop and implement a program to improve completers | Status 2 of 2 objectives are still in progress 5 of 5 action steps are in progress
Accomplishments A research and tracking system is being piloted in order to develop a dashboard to track CTE student progress toward completion. | 
Areas of Focus 2012-13 Continue to work on tracking system and dashboard with scheduled completion of January 2013. | 

## Slide 15: Strategic Plan 2010-2013 Summary of Progress
Goal 4.2: Establish an integrated and comprehensive economic and workforce development program. | 
Summary of Objectives and Action Steps Form collaborative partnerships Develop career ladders with industry and educational partners | Status 2 of 2 objectives are in progress 2 of 5 action steps are in progress
Accomplishments A comprehensive survey was deployed and data has been gathered on employer needs. Additionally, there is an annual Economic and Workforce Development Roundtable and more accountability and assessment of CTE program advisory groups. | 
Areas of Focus 2012-13 Completion of the analysis of the comprehensive survey of employer needs as well as developing a comprehensive list of prospective sector collaborators. | 

## Slide 16: Strategic Plan 2010-2013 Summary of Progress
Goal 4.3: Double the training services offered to faculty in the areas of teaching innovation and best teaching practices. | 
Summary of Objectives and Action Steps There is one objectives and 8 action steps associated with this goal: Expand the scope of the Institute for Teaching and Learning | Status 1 of 1 objectives are in progress 3 of 8 action steps are in progress
Accomplishments Resources and a permanent location for the ITL have been established. Additionally, funding to develop more faculty learning communities was also obtained. Faculty were trained in facilitation of faculty learning communities and a survey of faculty and student training needs was deployed and analyzed. | 
Areas of Focus 2012-13 Continue to pursue grants and other funding sources to further develop the ITL. Develop a timeline for visiting other college teaching and learning centers. | 

## Slide 17: Upcoming Activities
Communicate with “in-progress” areas
Process evaluation
Report at Winter In-service
  Focus on several metrics associated with some goals
New plan development Spring 2013
  Examination of internal data
  Environmental scan
  TracDat